## Dashboard
Integrated Development Project Controls
One control workbook for programme, cost, risk, action, decision and change governance
EXECUTIVE CONTROL POSITION
6 |  | Total records |  |  | Status | Count
[5 empty] | Open or active | 1
1 |  | Open or active |  |  | At risk | 0
[5 empty] | Complete | 0
0 |  | At risk |  |  | Other | 5
0 |  | Complete
MANAGEMENT REVIEW
Reporting period | Prepared by |  | Review date
Overall position | Top concern |  | Decision required
Programme | Cost |  | Risk
Commercial | Quality |  | Authority
Next review | Approved by |  | Issue status | Draft
Notes

## Project Setup
Project Setup
Integrated Development Project Controls
Field | Value | Owner | Review Date | Notes
Project Name | Development Project | Development Manager | 2026-09-01 | Replace with the approved project title
Approved Budget | 500000000 | Project Director | 2026-09-01 | Currency to be confirmed
Baseline Completion | 47118 | Planning Manager | 2026-09-15 | Use the approved baseline
Current Stage | Concept Design | Development Manager | 2026-09-01 | Update after each gate

## Master Schedule
Master Schedule
Integrated Development Project Controls
ID | Workstream | Milestone | Baseline Date | Forecast Date | Status | Owner | Dependency | Variance Days | Recovery Action
MS001 | Development | Business case approval | 2026-09-15 | 2026-09-20 | In Progress | Development Manager | Investment review | 5 | Close outstanding assumptions
MS002 | Design | Concept design approval | 2026-11-15 | 2026-11-22 | Not Started | Lead Consultant | Business case approval | 7 | Protect weekly review cycle
MS003 | Authority | Planning submission | 2026-12-10 | 2026-12-10 | Not Started | Authority Manager | Concept design approval | 0 | Confirm submission checklist
MS004 | Procurement | Main works tender issue | 2027-05-01 | 2027-05-18 | Not Started | Commercial Manager | Detailed design | 17 | Package early works separately
MS005 | Construction | Site mobilisation | 2027-08-01 | 2027-08-15 | Not Started | Project Manager | Contract award | 14 | Advance logistics planning
MS006 | Handover | Practical completion | 2028-12-31 | 2029-01-20 | Not Started | Project Manager | Testing and commissioning | 20 | Develop recovery programme

## Actions
Actions
Integrated Development Project Controls
Action ID | Date Raised | Action | Owner | Due Date | Priority | Status | Source | Age Days | Closeout Evidence
A001 | 2026-08-20 | Confirm updated product schedule | Development Manager | 2026-09-02 | High | In Progress | Design workshop | 8
A002 | 2026-08-22 | Issue utility demand assumptions | Infrastructure Consultant | 2026-09-05 | Medium | Not Started | Coordination meeting | 6
A003 | 2026-08-18 | Close pricing sensitivity | Investment Manager | 2026-08-30 | High | Complete | Investment review | 10 | Approved sensitivity sheet

## Risks
Risks
Integrated Development Project Controls
Risk ID | Category | Risk Statement | Cause | Impact | Probability | Impact Score | Risk Score | Owner | Response | Target Date | Status
R001 | Planning | Approval delay affects tender | Incomplete authority data | Programme | 4 | 4 | 16 | Authority Manager | Early authority workshop | 2026-09-20 | Open
R002 | Cost | Tender exceeds approved budget | Market escalation | Cost | 3 | 5 | 15 | Commercial Manager | Package benchmarking and value engineering | 2026-10-10 | Open
R003 | Market | Product absorption underperforms | Mismatch with demand | Revenue | 2 | 5 | 10 | Development Manager | Update market evidence and product mix | 2026-09-30 | Monitoring

## Decisions
Decisions
Integrated Development Project Controls
Decision ID | Date Raised | Decision Required | Options Considered | Recommendation | Decision Maker | Required By | Status | Decision | Impact
D001 | 2026-08-20 | Approve revised product mix | Base, premium, blended | Blended mix | Project Director | 46270 | Pending |  | Launch programme
D002 | 2026-08-22 | Confirm façade cost target | Original, value engineered | Value engineered | Development Director | 46273 | Pending |  | CAPEX

## Change Control
Change Control
Integrated Development Project Controls
Change ID | Date | Description | Originator | Reason | Cost Impact | Programme Impact Days | Revenue Impact | Status | Approver | Decision Date | Net Value Impact
C001 | 2026-08-15 | Increase selected unit areas | Development | Market positioning | 25000000 | 14 | 60000000 | Under Review | Project Director |  | 35000000
C002 | 2026-08-21 | Alternative façade material | Design | Value engineering | -12000000 | 0 | 0 | Approved | Development Director | 2026-08-25 | 12000000

## Cost Report
Cost Report
Integrated Development Project Controls
Cost Code | Package | Approved Budget | Committed | Forecast Final Cost | Variance | Paid to Date | Remaining Commitment | Status | Action
01 | Enabling works | 25000000 | 22000000 | 24000000 | 1000000 | 8000000 | 14000000 | On Budget | Monitor
02 | Main works | 300000000 | 0 | 318000000 | -18000000 | 0 | 318000000 | Over Budget | Value engineering
03 | Infrastructure | 90000000 | 15000000 | 92000000 | -2000000 | 5000000 | 87000000 | At Risk | Confirm scope boundary

## Monthly Report
Monthly Report
Integrated Development Project Controls
Reporting Period | Executive Summary | Programme Position | Cost Position | Key Decisions | Top Risks | Next Period Priorities | Prepared By | Issue Date
Aug 2026 | Complete the development and consultant status narrative. | Record critical milestone movement. | Record budget and forecast movement. | List decisions requiring executive action. | List the three risks that can change the business case. | State the five priorities for the next period. | Development Manager | 2026-08-31

## Read Me
Integrated Development Project Controls
Professional working resource by Mina Nady Farhan
HOW TO USE THIS WORKBOOK
1. Complete the project setup and confirm the reporting period. 2. Replace the worked example rows with live project information. 3. Keep one accountable owner and one due date against every open control item. 4. Update status and evidence during the formal project review cycle. 5. Use the dashboard for management discussion, not as a substitute for the underlying registers. 6. Archive approved reporting periods before major baseline changes. The workbook is a professional working template. It does not replace the approved contract, programme, cost plan or governance procedure.